## Action Plan
Great Blakenham Parish Council — Internal Audit Action Plan
Internal Audit Report for the period ending 31 March 2026 ¦ Prepared from the auditor's recommendations and comments
ID | Area | Priority | Action / Recommendation | Lead | Owner / Approval | Status | Date Completed | Target / Frequency | Audit Reference
1 | Standing Orders | High | Remove/complete all round and square brackets and tailor the NALC model Standing Orders to the Council. | Clerk / Full Council | Full Council | Closed | 10.09.26 | Before next review/meeting cycle | L68-L84
2 | Financial Regulations | High | Remove remaining square brackets and adapt the Financial Regulations to the Council. | Clerk / Full Council | Full Council | Open |  | Before next review/meeting cycle | L85-L105
3 | Budgetary controls | High | Introduce regular statements comparing budgeted and actual income/expenditure, in line with Standing Order 17c, to support virements and oversight. | Clerk / RFO | Full Council | Open |  | Quarterly | L149-L158
4 | Budget setting | Medium | Ensure minutes clearly record the final agreed budget figure and the reasoning behind it; upload a clear budget document. | Clerk | Full Council | Open |  | Next budget-setting cycle | L131-L143
5 | General reserves | High | Review the purpose and level of the high general reserve and consider whether long-term projects/needs should be earmarked. | Full Council / RFO | Full Council | Open |  | Next reserves review | L165-L184
6 | Reserves Policy | Medium | Upload the reviewed Reserves Policy adopted 12 March 2026 so the website carries the current version. | Clerk | Full Council | Open |  | As soon as practicable | L165-L184
7 | Statutory powers | Medium | Review powers used for expenditure and record the appropriate statutory power for relevant items. | Clerk / RFO | Full Council | Open |  | Ongoing / next review | L223-L238
8 | VAT | High | Revisit the cashbook, correctly record VAT in Rialtas, and make appropriate VAT reclaims. Year-end VAT balance identified as £685.15 still to claim. | RFO | Full Council | Open |  | As soon as practicable | L282-L301
9 | Donations / s137 | High | Review the legal power used for donations; use s137 where appropriate and clearly identify s137 expenditure in minutes and payments lists. | Clerk / RFO | Full Council | Open |  | Before next relevant payments/minutes | L302-L336
10 | CIL | High | Reconcile the CIL earmarked reserve/cashbook figures with the reported 2024/25 retained balance of £64,472.70. | RFO / Clerk | Full Council | Open |  | As soon as practicable | L375-L396
11 | CIL annual report | High | Produce and publish the 2025/26 CIL annual report. | Clerk / RFO | Full Council | Open |  | As soon as practicable | L375-L396
12 | Investment policy | Future | Consider adopting an investment policy covering objectives, investments, reporting and review, given bank balances above £100,000. | Full Council / RFO | Full Council | Open |  | Future agenda | L441-L454
13 | Internal Control Report | High | Adopt an Internal Control Report to demonstrate annual review/effectiveness of internal controls and inform the Annual Governance Statement. | Clerk / Full Council | Full Council | Open |  | Before next AGS | L672-L688
14 | Internal audit effectiveness | High | Review the internal audit terms of reference and effectiveness, including the Council's understanding of internal audit's role, and evidence the review. | Full Council | Full Council | Open |  | Before next AGS | L689-L700
15 | Asset Register / AGAR | High | Review AGAR Section 2 line 9 and reconcile it to the Asset Register; line 9 should include fixed assets, long-term investments and debtor long-term loans. | Clerk / RFO | Full Council | Open |  | Before next AGAR | L747-L774
16 | Asset Register review | High | Carry out and minute an annual review of the Asset Register. | Clerk / RFO | Full Council | Open |  | Annually | L747-L774
17 | Publication Scheme | High | Review the Publication Scheme, ensure it reflects current activities/information availability, add adoption/review dates, and keep website information current. | Clerk | Full Council | Open |  | As soon as practicable / annual review | L810-L831
18 | GDPR | High | Adopt/maintain the Privacy Policy, Subject Access Request procedure, FOI request procedure and Data Breach procedure; evidence reviews and provide appropriate training/audits. | Clerk / Data lead | Full Council | Open |  | As soon as practicable / ongoing | L841-L890
19 | Transparency Code | High | Consider/implement required website publication: quarterly individual expenditure over £500, Government Procurement Card transactions, invitations to tender over £5,000, contracts over £5,000; annual assets, VCSE grants and organisational chart. | Clerk / RFO | Full Council | Open |  | Quarterly / annually | L891-L919
20 | Accessibility statement | High | Publish a website accessibility statement covering non-compliance reasons, alternative access to documents, contact arrangements and review arrangements. | Clerk | Full Council | Open |  | As soon as practicable | L926-L947
21 | Accessibility testing | High | Carry out and record the annual website accessibility test; previous test was November 2024. | Clerk | Full Council | Open |  | Annually | L926-L947
22 | IT Policy | High | Formally adopt a tailored IT policy and mandate authority-owned email for official Council business. | Full Council / Clerk | Full Council | Open |  | As soon as practicable | L971-L988
23 | Electronic backups | High | Verify or establish an appropriate electronic backup arrangement and retain evidence of the arrangement/testing. | Clerk | Full Council | Open |  | As soon as practicable / ongoing | L1160-L1163
24 | Previous internal audit | High | Formally consider the 2024/25 Internal Audit Report at Full Council and record the consideration in the minutes. | Clerk / Chair | Full Council | Open |  | Next Full Council meeting | L1019-L1072
25 | Outstanding 2024/25 recommendations | High | Work through the outstanding prior recommendations: precept figure in minutes; quarterly budget monitoring; reserves; accounting statement corrections/approval; AGS Section 1 before Section 2; correct website form; correct public rights notice; direct link to District Council page. | Clerk / RFO / Full Council | Full Council | Open |  | Action tracker until complete | L1027-L1068
26 | Outstanding 2023/24 recommendation | Medium | Review high general reserves and minute the Council's intention regarding their purpose/use. | Full Council | Full Council | Open |  | Next reserves review | L1069-L1072
27 | Minutes numbering | Medium | Introduce consecutive page numbering for loose-leaf minutes. | Clerk | Full Council | Open |  | Immediately / ongoing | L1127-L1139
28 | Register of Interests link | Medium | Add a website link to the Register of Interests on the District Authority website. | Clerk | Full Council | Open |  | As soon as practicable | L1140-L1147
29 | Trust funds / AGAR | Medium | Review AGAR Section 2 line 11 and the disclosure regarding trust funds, following the auditor's comment on the Council's trustee responsibilities. | Clerk / Full Council | Full Council | Open |  | Before next AGAR | L1148-L1154
30 | Pension re-enrolment | Future | Ensure the Council meets the 2027 pension re-enrolment/re-declaration deadlines. | Clerk / Payroll | Full Council | Open |  | 2027 deadline | L521-L527

## Dashboard
Internal Audit Action Plan — Dashboard
Total actions | 30 | Suggested review rhythm
High priority | 21 | At each Full Council meeting
Medium priority | 7 | Review open / in-progress actions and record updates in minutes.
Future | 2
Open | 29 | Quarterly
In Progress | 0 | Budget monitoring and Transparency Code publication checks.
Complete | 0
Deferred | 0 | Annually
Internal controls, internal audit effectiveness, asset register and accessibility review.

## How to Use
How to use this action plan
1 | Assign a named lead and agree the target date/frequency at Full Council.
2 | Update Status and Date Completed as actions progress.
3 | For each completed action, retain evidence (minutes, adopted policy, published webpage, reconciliation, report, etc.).
4 | Use the Audit Reference column to locate the supporting recommendation/comment in the Internal Audit Report.
5 | Keep this spreadsheet as the live action tracker and report progress to Full Council.